## Pre-requisites
Exchange 2013 Hybrid Upgrade to Exchange 2019
ID | Description
1 | Administrator Access – (Enterprise/Schema/Domain/Organization Management)
2 | Latest security updates installed on the OS
3 | Export the current certificate from the Exchange 2013
4 | Load balancer VIP for Exchange 2019
5 | Firewall port communication for the below, • Exchange 2013 and Exchange 2019 • Email gateway solution and Exchange 2019 • Applications and Exchange 2019 for Relay • User subnets to the Exchange 2019 VIP • Exchange 2019 and Office365 for Hybrid Configuration
6 | Azure AD Connect Server Access to refresh the Directory schema in case of any errors in AAD sync
7 | M365 Global administrator login to re-run the Hybrid configuration wizard
8 | Export the current Hybrid Configuration

## Implementation Steps
Exchange 2013 Hybrid Upgrade to Exchange 2019
ID | Activities
1 | Install the below pre-requisites on the Exchange 2019 server, • Install .NET Framework 4.8 • Visual C++ Redistributable Package for Visual Studio 2012 • Visual C++ Redistributable Package for Visual Studio 2013 • Install-WindowsFeature Server-Media-Foundation • Install Unified Communications Managed API 4.0 • Install-WindowsFeature Server-Media-Foundation, NET-Framework-45-Features, RPC-over-HTTP-proxy, RSAT-Clustering, RSAT-Clustering-CmdInterface, RSAT-Clustering-Mgmt, RSAT-Clustering-PowerShell, WAS-Process-Model, Web-Asp-Net45, Web-Basic-Auth, Web-Client-Auth, Web-Digest-Auth, Web-Dir-Browsing, Web-Dyn-Compression, Web-Http-Errors, Web-Http-Logging, Web-Http-Redirect, Web-Http-Tracing, Web-ISAPI-Ext, Web-ISAPI-Filter, Web-Lgcy-Mgmt-Console, Web-Metabase, Web-Mgmt-Console, Web-Mgmt-Service, Web-Net-Ext45, Web-Request-Monitor, Web-Server, Web-Stat-Compression, Web-Static-Content, Web-Windows-Auth, Web-WMI, Windows-Identity-Foundation, RSAT-ADDS
2 | Reboot the server
3 | Verify the AD attributes - rangeUpper, Objectversion before preparing the AD for Exchange 2019
4 | Prepare the AD schema using Setup /prepareSchema /IAcceptExchangeServerLicenseTerms
5 | Prepare the AD using Setup /prepareAD /IAcceptExchangeServerLicenseTerms
6 | Prepare the AD domains using Setup /prepareAllDomains /IAcceptExchangeServerLicenseTerms
7 | Verify the AD attributes - rangeUpper, Objectversion for Exchange 2019
8 | Refresh the Directory schema using the AAD Connect – in case of any errors in AAD sync
9 | Install the Exchange 2019 using Setup.exe either using GUI or unattended setup
10 | Reboot the server
11 | Verify the Exchange installation by using the https://localhost/ecp
12 | Follow the steps 01, 02 & 09 - 11 on the other servers one by one if any
13 | Activate the Microsoft Exchange 2019 Servers
14 | Import the wildcard certificate to the Exchange 2019 servers
15 | Assign the services to the certificate
16 | Configure the AutoD SCP for Exchange 2019 servers using Set-ClientAccessService -AutoDiscoverServiceInternalURI
17 | Configure the Internal URL & External URL for the Exchange 2019 Virtual directories and OA using EAC or PS • OA • ECP • OWA • EWS • EAS • MAPI • OAB
18 | Create the DAG and add the Exchange 2019 members to it
19 | Create the Databases by specifying the database & log files location (Quotas to be noted)
20 | Add the mailbox database copies to the DAG with correct Activation preference
21 | Verify the OAB in Exchange 2019
22 | Enable IMAP & POP if required
23 | Verify the Accepted domains are populated
24 | Verify the Receive Connectors in the Exchange 2019 and create the required custom receive connectors like Exchange 2013
25 | Create a new test mailbox in Exchange 2013
26 | Perform client connectivity/mail flow - internal/external
27 | Move the same mailbox to Exchange 2019
28 | Perform tests by adding host file entry to the VIP of Exchange 2019 client connectivity/mail flow - internal/external. External email will go through Exchange 2013 at this time
29 | Verify If the Applications can connect (if any) and send emails using Exchange 2019 VIP
30 | Email gateway solution to be configured with new Exchange 2019 IP's for send/receive emails
31 | Add the Exchange 2019 servers to the Send Connector as the Source servers
32 | External Public IP to be NAT’ed to the VIP of Exchange 2019 (This would allow not to change public DNS and in case of any issue, this can be changed to the existing VIP of Exchange 2013)
33 | Internal DNS name to be changed to new VIP of Exchange 2019
34 | Perform all the tests for users connecting to Exchange 2019 with their mailboxes on Exchange 2013
35 | Re-run the Hybrid Configuration Wizard
36 | Create the migration batches and start moving the mailboxes
37 | Move the Public folders/Public folder mailboxes (if any)
38 | once all mailboxes are migrated, power off Exchange 2013 servers and monitor it for a week
39 | Power on the Exchange 2013 servers
40 | Uninstall Exchange 2013 servers using GUI or unattended setup mode

## Rollback Plan
Exchange 2013 Hybrid Upgrade to Exchange 2019
ID | Activities
1 | Uninstall Exchange 2019 incase if issues arise before the services migration
2 | Change the NAT from public IP to Existing Exchange 2013 so services stay in Exchange 2013
3 | Change internal DNS back to Exchange 2013
4 | Change the Email gateway solution to send/receive emails to Exchange 2013
5 | Remove the Exchange 2019 servers from send connector and add Exchange 2013
6 | Application teams to connect to Exchange 2013 VIP
7 | Set the AutodiscoverServiceInternalURI to Null on the Exchange 2019 servers